## Project schedule
Updated 5 Year Plan November 2025 |  |  |  | 2024 |  |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
|  |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
TASK | WHO? | START | END | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
LEASE | SO, FS
Explore Lease options and discuss them with Advisory Committee DONE | HDCC | 2024-10-01 | 2024-12-01 | bar: Q4 O to Q4 N
Advisory committee/PC agree preferred lease option DONE | PC | 2024-12-01 | 2025-02-01 | bar: Q4 D to Q1 J
Brief Parish Clerk re HDCC Lease requirements - DONE | SP | 2024-12-01 | 2024-12-31 | bar: Q4 D
Agree process & parties for lease resolution DONE | Adv Comm | 2025-01-01 | 2025-03-01 | bar: Q4 D to Q1 J
Initiate Lease negotiations with PC, HDCC and HDPFA DONE | FS SP | 2024-12-01 | 30/02/2025 | bar: Q1 J to Q1 F
All parties agree Heads of Terms DONE | HDCC/HDPF/PC | 2025-02-01 | 2025-03-31 | bar: Q1 F to Q1 M
Prepare Draft Lease Feb/Mar - DONE |  | 2025-02-01 | 2025-03-31 | bar: Q1 F to Q1 M
Instruct Solicitors DONE | PC HDCC | 2025-03-01 | 2025-03-31 | bar: Q2 M to Q2 J
All parties sign new leases delayed from Mar 25 to November 25 CRITICAL PATH | HDCC/HDPFA/PC | 2024-10-01 | 2026-02-01 | bar: Q2 M to Q1 F
GOVERNANCE | SP, MC
Take advice from AIRS - ONGOING | HDCC | 2024-10-01 | 2027-01-01 | bar: Q4 O to Q4 D
Discuss HDPF as a CIO with charity commission HDPF DECIDED NOT TO PROCEED AT THIS STAGE | FS | 2024-10-01 | 2025-03-11 | bar: Q1 J to Q1 M
Engage with HDPFA and PC on governance solution SUPERCEDED BY LEASE DECISION | SP MC | 2024-10-01 | 2025-03-30 | bar: Q4 O to Q1 M
Business Plan Update - DELAYED PENDING PARISH POLL | MC SP | 2025-11-01 | 2026-01-01 | bar: Q4 N to Q4 D; Q2 A to Q2 J; Q2 A to Q2 J; Q2 A to Q2 J
Establish and review risk register TO BE UPDATED | SP/MC | 2025-10-01 | 2025-11-11 | bar: Q4 O to Q4 D; Q2 A to Q2 J; Q2 A to Q2 J; Q2 A to Q2 J
Agree joined up fundraising strategy for village orgs DONE | HDCC | 2025-02-01 | 01/032025 | bar: Q1 F; Q1 F
Advisory Committee Meetings | Ad Com | bar: Q4 N; Q1 J; Q1 M; Q2 M; Q3 J; Q3 S; Q4 N; Q1 J; Q1 M; Q2 M; Q3 J; Q3 S; Q4 N; Q1 J; Q1 M; Q2 M; Q3 J; Q3 S; Q4 N; Q1 J; Q1 M; Q2 M; Q3 J; Q3 S; Q4 N; Q1 J; Q1 M; Q2 M; Q3 J; Q3 S; Q4 N
Agree Policy for Management of Grant Funds with Advisory Committee | HDCC | 2025-12-01 | 2025-11-11 | bar: Q4 N
Take professional advice on creation of Fund holding investment policy | HDCC | 2025-09-20 | 2025-11-11 | bar: Q3 S to Q4 N
Advertise for and appoint new finance trustee role to manage new fund holding governance | HDCC | 2025-10-01 | 2026-03-01 | bar: Q4 N
Hold Mid Project Review - Go / No-Go CRITICAL PATH | HDCC | 2026-11-01 | 2026-12-31 | bar: Q4 D to Q1 F
AGM | HDCC | Feb | bar: Q1 F; Q1 F; Q1 F; Q1 F; Q1 F
Confirm plan for HDVH | HDCC HDVH | 2026-12-01 | 2027-02-01 | bar: Q4 D to Q1 F
Confirm HDPF Interim Plan | HDCC HDPF | 2027-01-01 | 2027-04-01 | bar: Q1 J to Q1 M
Confirm Phase 2 Plan | Ad Com | 2027-01-01 | 2027-04-01 | bar: Q1 F to Q1 M
Transition Plan agreed to include - handover of equipment, customers, staff | Ad Com | 2027-11-01 | 2028-06-01 | bar: Q4 O to Q2 M
Register with HMRC for in anticipation of claiming VAT back | HDCC | 2026-01-01 | 2026-07-01 | bar: Q1 J to Q2 J
Ensure written confirmation from HMRC on vat status | HDCC | 2026-03-01 | 2026-05-01 | bar: Q2 A to Q2 J
Ensure essential funds in place (at least £750k) CRITICAL PATH | HDCC | 2026-12-01 | 2027-01-01 | bar: Q4 D to Q1 J
Launch local fundraising to close the gap | HDCC | 2026-12-01 | 2027-08-01 | bar: Q4 D to Q2 J
Liaise with PC on Village Referendum on plan for existing hall NEED TO AGREE TIMING WITH PC | PC | 2026-07-01 | 2027-02-01 | bar: Q3 S to Q1 J
AIRS training and mentoring for trustees on managing new facility | HDCC | 2028-05-01 | 2028-07-01 | bar: Q2 M to Q2 J
Agree and execute ops plan for new community centre | HDCC HDVH HDPA | 2028-07-01 | 2029-03-01 | bar: Q3 J to Q1 F
Once open. Monitor and evalualtion of HDCC to measure usage and report back to funders (as per agreememt) | HDCC | 2029-03-01 | 2030-03-01 | bar: Q1 M to Q4 D
FUNDRAISING | BL, SP, MC
Establish village calendar | GL/JT/DH | 2024-10-01 | 2024-11-01 | bar: Q4 O
Ongoing program of local events to build community spirit and raise funds ONGOING | GL/JT/DH | 2024-10-01 | 2029-01-01
Maintain Just giving page and village lottery ONGOING | SP JTo | 2024-10-01 | 2029-01-01
"Friends of HDCC" campaign to raise funds for detailed technical drawings/costings CRITICAL PATH | HDCC Jules | 2026-01-01 | 2026-04-01 | bar: Q1 J to Q1 M
Research grant making organisations IN PROGRESS | Bob/Jules | 2024-12-01 | 2025-04-01 | bar: Q4 N to Q1 M
Continue to develop fundraising strategy IN PROGRESS | HDCC | 2025-04-01 | 2028-07-01 | bar: Q4 N to Q3 S
Apply to corporate sponsors for funding for professional fees and feasability support - STARTED | HDCC | 2025-10-01 | 2026-12-01 | bar: Q3 S to Q4 D
Recruit and train local fundraising volunteers | HDCC | 2026-02-01 | 2026-05-01 | bar: Q1 F to Q2 J
Launch major grant funding drive (once lease/gov in place) | HDCC | 2025-11-11 | 2026-12-01 | bar: Q1 M to Q4 D
Liaise with local govt on funding opportunities and CIL APPLICATION TBD CRITICAL PATH | HDCC | 2025-05-01 | 2025-12-01 | bar: Q2 M to Q4 D
Identify and engage with local sponsors and benefactors | HDCC Jules | 2025-10-01 | 2026-12-01 | bar: Q4 O to Q4 D
Contact High Net worth individuals | HDCC Jules | 2026-02-01 | 2026-12-01 | bar: Q1 F to Q4 D
Put visible tracker in place | HDCC | 2026-01-01 | 2026-12-01 | bar: Q1 J to Q4 D
Agree Policy for Management of Grant Funds with Advisory Committee | HDCC | 2026-09-20 | 2026-03-01 | bar: Q4 N to Q1 F
Take professional advice on creation of Fund holding investment policy | HDCC | 2025-09-20 | 2026-03-01 | bar: Q4 N to Q1 F
Advertise for and appoint new finance trustee role to manage new fund holding governance | HDCC | 2025-10-01 | 2025-12-01 | bar: Q4 D to Q1 F
Launch community and crowd fund contributer program - "Buy a brick" | HDCC | 2026-12-01 | 2026-12-31 | bar: Q4 N to Q4 D
Identify Anchor tenants | HDCC | 2027-10-01 | 2028-01-01 | bar: Q4 O to Q4 D
Ensure sufficient funds for year 1 operation BRING FORWARD CRITICAL PATH | HDCC | 2028-01-01 | 2028-03-01 | bar: Q1 J to Q1 F
Claim VAT on Phase 1 to initiate Phase 2 build | HDCC | 2028-10-01 | 2028-12-31 | bar: Q4 O to Q4 D
MARKETING & COMMS
Create marketing materials to drive fundraising "help build the hall" DONE | SP | 2024-01-01 | 2025-02-01 | bar: Q4 O to Q1 J
Kick of Village engagement strategy - set up working teams DONE | MC/SP | 2024-11-01 | 2025-02-01 | bar: Q4 D to Q1 J
Create Donation QR code DONE | SP | 2024-12-01 | 2025-01-01 | bar: Q4 D
Monthly article in village magazine ONGOING | SP | 2025-01-01 | 2029-01-01
Engage with Buxted & Blackboys | BL | 2026-01-01 | 2026-04-01 | bar: Q1 J to Q1 M
Engage with St Marks | SP MC | 2026-01-01 | 2026-04-01 | bar: Q1 J to Q1 M
Engage with local politicians DONE | SP | 2025-01-01 | 2025-03-01 | bar: Q1 J to Q1 M
Tripartate meeting - closer links with PC and HDVH - DONE | PC | 2025-02-01 | 2025-03-01 | bar: Q1 J; Q1 F; Q1 J
Grow HDCC social media presence ONGOING | HDCC | 2025-04-01 | 2026-01-01 | bar: Q2 A to Q2 J
3D walk through new centre | HDCC | 2026-01-01 | 2026-04-01 | bar: Q1 J to Q1 M
BUILD & DESIGN
Obtain formal extant planning approval - WD/2018/2655/MAJ | HDCC | 2024-10-01 | 2025-01-01 | bar: Q4 O to Q4 N
Project brief, business case, site appraisals, outline budget and cost plan, stakeholder feedback, site surveys and info, architectural concept and outline specification DONE | HDCC/MJB | 2024-10-01 | 2025-01-01 | bar: Q4 O to Q4 D
Undertake mechanical eng analysis - DONE | PS | 2025-01-01 | 2025-04-01 | bar: Q1 J to Q1 M
Review building working team membership and expert advisors | HDCC | 2025-11-01 | 2026-01-01 | bar: Q4 N to Q1 J
Formalise "Plan for Use" Strategy through stakeholder enagement sessions | HDCC | 2026-01-01 | 2026-11-01 | bar: Q1 F; Q2 M; Q3 A; Q4 N
Undertake a design review based on updated Plan for Use | HDCC | 2026-01-01 | 2026-03-01 | bar: Q2 A to Q3 J
Develop capital governance /project cost plan - including detailed drawings, costings etc CRITICAL PATH | HDCC/MJB | 2026-03-01 | 2026-06-01 | bar: Q2 M to Q3 J
Develop a set of construction information for potential building contractors | HDCC/MJB | 2026-05-01 | 2026-09-01 | bar: Q3 J to Q4 O
Prepare tender | MJB/HDCC | 2026-11-01 | 2027-04-01 | bar: Q4 N to Q1 M
Identify prefrerred contractors | MJB/HDCC | 2026-09-01 | 2026-12-01 | bar: Q3 S to Q4 D
Award the Building Contract | MJB/HDCC | 2027-03-01 | 2027-05-01 | bar: Q1 M to Q2 M
Create project risk and contingency for build phase and identify insurance required | PC/MJB/HDCC/Contractor | 2027-04-01 | 2027-09-01 | bar: Q2 A to Q3 A
Prepare fire safety and H&S strategy for construction phase | PC/MJB/HDCC/Contractor | 2027-04-01 | 2027-09-01 | bar: Q2 A to Q3 A
Obtain consents required prior to construction - LA, planning PC | HDCC | 2027-04-01 | 2027-09-01 | bar: Q2 A to Q3 A
Construct the building and groundworks incl car park | CONTRACTOR | 2027-09-01 | 2028-09-01 | bar: Q4 O to Q3 J
Regular site visits/inspections by building control – Project manager -1.9.27 - 1.9.28 | Proj Mgr | 01/0927 | 2028-09-01 | bar: Q4 O to Q3 J
Inspect the construction as it progresses | HDCC | 2027-09-01 | 2028-09-01 | bar: Q2 M to Q1 M
Procure hall equipment and furnishing - final fit out | HDCC | 2028-09-01 | 2028-12-01 | bar: Q2 M to Q1 M
Handover the building | HDCC | 2028-09-01 | 2029-03-01 | bar: Q4 O to Q2 A
Key in door | HDCC | 2029-03-01 | 2029-04-01 | bar: Q2 A
Formulas:
START = [END, row above]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.